Standard Annotation Procedure

Revision 1

08/29/2019

CONTENTS

Phase I	Phase II	Phase III	Phase IV	Phase V

| Phase I | 2 |
| --- | --- |

Planning

- Start with a literature review, being sure to look for: o Preexisting corpora

o  Preexisting guidelines

o  General literature related to topic

- Approach domain experts once some preliminary literature review has been completed

- Define the nature of the annotation task:

- Concept level?

- Document level?

  - Patient level?

- Define a minimum Kappa score that must be reached before proceeding with production

- Delegate primary arbitrator (usually a PI) for reconciling disagreements, e.g. decisions about the direction of the study, what concepts to include/exclude, how to approach definitions, etc.

- Draft a list of potential annotators and contact them to get a sense of their workload

- Refer to the following documents to help with creation of your Annotation Guide:

  - 2Instuctions_AnnotationGuideCreation.pdf

  - 3Template_AnnotationGuide.docx

- The following Sections should be completed before moving on to Phase II:

  - I-1 Background

- I-2 Annotation Tool

- I-3 Instructions

- I-4 Definitions

- II-1 Meeting Notes

- II-3 References

*It is recommended that you start drafting your Annotation Guide early in the Planning Phase; it is OK and expected that it be rough at this point*

Back to CONTENTS

Standard Annotation Procedure | Updated by LAC on 08/29/2019 | Rev 1

| Phase II | 3 |
| --- | --- |

Training

- Have a preliminary meeting with your annotators, discussing the overall goal of your study and going through the contents of your Annotation Guide draft

- Allow annotators to become familiar with the Annotation Tool and Definitions of interest, having them work on a sample of 5-10 notes on their own

- Another meeting should be held within a week to follow up on these initial annotation activities and should mostly focus on addressing issues with the Tool if present

- Annotators should feel comfortable with the Tool before moving on to Phase III

Back to CONTENTS

Standard Annotation Procedure | Updated by LAC on 08/29/2019 | Rev 1

| Phase III | 4 |
| --- | --- |

Development

- Sample ~10% of the total notes in your data set, and use this “Development Set” for the remainder of Phase III

- Run through 3-5 iterations (more if needed) of annotation/adjudication on sub-sets of the Development Set

- Calculate IAA after each iteration

- Meet after each iteration with as many stakeholders as possible to address Issues/Questions, Insights/Answers, and Updates; use Section II-1 to document

- Refine the Annotation Guide liberally and continuously, being sure to update the Revision number and Date every time a change is made

- Utilize the arbitrator to reconcile high-level disagreements

- IAA must equal the pre-defined Kappa score before moving on to Phase IV

Back to CONTENTS

Standard Annotation Procedure | Updated by LAC on 08/29/2019 | Rev 1

| Phase IV | 5 |
| --- | --- |

Production

- Divide the remaining “Production Set” of data between a minimum of two annotators with a minimum of 40% overlap; more annotators and/or overlap is recommended as time and money permit

- Around 2-3 iterations should be completed, calculating IAA after each

- At least 1 mid-point check-in meeting should be held to address any concerns that have arisen and to ensure things are on track

- GENERAL: because there cannot be any a priori recommendations as to the number of documents, patients, etc. required for a particular study, we generally say that there should be enough data to satisfy a statistically robust analysis

- Phase IV is finished once the entire, statistically robust Production Set has been annotated

Back to CONTENTS

Standard Annotation Procedure | Updated by LAC on 08/29/2019 | Rev 1

| Phase V | 6 |
| --- | --- |

Wrap-Up

- Hold a final review meeting with as many stakeholders as possible

- Discuss and record lessons learned if any

- Discuss and complete archiving and sharing of data/guide if applicable

- Complete final summary analysis of annotation

Back to CONTENTS

Standard Annotation Procedure | Updated by LAC on 08/29/2019 | Rev 1